## Sheet1
Milestones | Details | Deadline
Custom Milestone 1 | Finish up All Frontend Side | 2020-11-01
Custom Milestone 2 | Finish up All Backend Side | 2020-11-10
Milestone 7 | Progress Update | 2020-11-17
Milestone 8 | Final Presentation | 2020-12-16
Categories | Task Lists | Deadline or Expected | Member assigned
Front End Development | HTML/CSS | 2020-11-01
| Admin Side (Add Users/Orders/Delete/View) | 2020-10-28 | Alex
| User Side (Settings/About) | 2020-10-29 | Alex
| Main Website (Home) | 2020-10-30 | Sachin
| Carts (Add/Delete/View) | 2020-10-28 | Rob
| Products (Add/Delete/View) | 2020-10-29 | Sachin
| Login/Logout | 2020-10-30 | Rob
Back End Development | PHP | 2020-11-01
| Admin Side (Add Users/Orders/Delete/View) | 2020-11-03 | Alex
| User Side (Settings/About) | 2020-11-04 | Alex
| Main Website (Home) | 2020-11-03 | Sachin
| Carts (Add/Delete/View) | 2020-11-04 | Rob
| Products (Add/Delete/View) | 2020-11-04 | Sachin
| Login/Logout | 2020-11-05 | Rob
Database Development | SQL | 2020-11-01
| Admin Side (Add Users/Orders/Delete/View) | 2020-11-13 | Alex
| User Side (Settings/About) | 2020-11-14 | Alex
| Main Website (Home) | 2020-11-13 | Sachin
| Carts (Add/Delete/View) | 2020-11-14 | Rob
| Products (Add/Delete/View) | 2020-11-14 | Sachin
| Login/Logout | 2020-11-15 | Rob