## Sheet1
Milestones | Details | Deadline
Custom Milestone 1 | Finish up All Frontend Side | 2020-11-01
Custom Milestone 2 | Finish up All Backend Side | 2020-11-10
Milestone 7 | Progress Update | 2020-11-17
Milestone 8 | Final Presentation | 2020-12-16
Categories | Task Lists | Deadline or Expected | Member assigned
Front End Development |  | 2020-11-01
| Admin Side | 2020-10-28 | Rob
| User Side | 2020-10-29 | Sachin
| Main Website | 2020-10-30 | Alex
Back End Development |  | 2020-11-10
| Admin Side | 2020-11-03 | Alex
| User Side | 2020-11-04 | Sachin
| Main Website | 2020-11-05 | Rob
Database Side Development |  | 2020-11-30
| Main Products | 2020-11-15 | Sachin
| User logon | 2020-11-17 | Rob
| Admin Side | 2020-11-24 | Alex